## Sheet1
|  |  |  | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | 2018-12-23 | ... | 2019-01-01 | ... | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30
Task Number | Task Name | Status | Time
Task 1 | Planning | 3 | 1 | 3
Task 2 | Design | 3 | 5 |  | 3 | 3 | 3 | 3 |  | 3
Task 3 | Development | 2 | 11 | [8 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1
Task 4 | Closeout - Lessons Learned | 1 | 3 | [19 empty] | 1 | 1 | 1
Task 1 | Planning | 3
Task 1.1 | Meeting | 3
Task 1.2 | Functional Specs | 3
Task 1.3 | Technical Specs | 3
Task 1.4 | Gantt Chart | 3
Task 2 | Design | 3
Task 2.1 | Choosing Imagery | 3
Task 2.2 | Adobe XD Prototype | 3
Task 2.3 | Design Proposal and Approval | 3
Task 2.4 | Potential Redesign | 3
Task 3 | Development | 2
Task 3.1 | File Structure | 2
Task 3.2 | Website Development | 2
Task 3.3 | Website Proposal and Approval | 1
Task 3.2 | Website Development | 2
Task 3.2.1 | Header | 3
Task 3.2.2 | Footer | 3
Task 3.2.3 | Home - Main Content | 3
Task 3.2.4 | About Us - Main Content | 3
Task 3.2.5 | Contant Us - Main Content | 2
Task 3.2.6 | PHP - Mailing system | 1
Task 3.2.7 | Maskinpark - Main Content | 1 | D
Task 3.2.8 | Responsive - Finetuning | 2
Task 4 | Closeout - Lessons Learned | 1
Task 4.1 | Description | 1
Task 4.2 | Analysis | 1
Task 4.3 | Recommendation | 1